## Sheet1
# | Screen/Module | Issue | Observed Result | Additional remark | Reported By | Status | Fixed By | Fixed Remark
1 | Category | Please remove "Remove" button from Category. |  | It will impact the application | JV
2 | Vendor | 1. Add new category 2. Goto vendor screen 3. Select the existing Category with vendors 4. Select the newly added Category | 1. Exception at step 4. After this exception, any Category you, there will be no data displayed and hits exception Exception in thread "AWT-EventQueue-0" java.lang.NullPointerException at sg.edu.nus.iss.se23pt2.pos.gui.AbstractStoreTableModel.getRowCount(AbstractStoreTableModel.java:31) at javax.swing.JTable.getRowCount(Unknown Source) at javax.swing.plaf.basic.BasicTableUI.createTableSize(Unknown Source) at javax.swing.plaf.basic.BasicTableUI.getPreferredSize(Unknown Source) at javax.swing.JComponent.getPreferredSize(Unknown Source) at javax.swing.JViewport.getViewSize(Unknown Source) at javax.swing.plaf.basic.BasicScrollPaneUI.syncScrollPaneWithViewport(Unknown Source) at javax.swing.plaf.basic.BasicScrollPaneUI$Handler.stateChanged(Unknown Source) at javax.swing.JViewport.fireStateChanged(Unknown Source) at javax.swing.JViewport.setView(Unknown Source) at javax.swing.JScrollPane.setViewportView(Unknown Source) at sg.edu.nus.iss.se23pt2.pos.gui.VendorPanel.showVendorsForSelectedCategory(VendorPanel.java:123) at sg.edu.nus.iss.se23pt2.pos.gui.VendorPanel$1.actionPerformed(VendorPanel.java:48) at javax.swing.JComboBox.fireActionEvent(Unknown Source) at javax.swing.JComboBox.setSelectedItem(Unknown Source) | 1. Is there any option to show the dropdown arrow head (the downward pointing arrow head)? Currently it appears as a readonly textbox | JV
3 | Vendor | 1. Rearrange vendors | Functionality missing after changing to table UI |  | JV
4 | Vendor | 1. Select more than one vendor 2. Click "Remove" button | 1. Hits exception | Either allow multiple deletes or allow only one selection at a time | JV
5 | Product | 1. The table displays product id with correct format as per requirement 2. Click "Add" button | 1. The product id displays with different format | Create product ID only when it is saved. This will avoid creating throwaway sequence numbers | JV
6 | Product | 1. Barcode should be non-editable | Currently it is editable | The barcode will be auto-generated (usually it is product id/code) and the barcode stickers will be printed out after adding the product | JV
7 | Product | Remove the "Remove" button |  | It will impact the application | JV
8 | Product | 1. Category column in table is not needed 2. Instead "Product Id", just "Id" can be used to get more space |  | It squeezes the table | JV
9 | Discount | 1. "Applicable to" column and dropdown should display "ALL" or "Member" |  | Can convert to values "A" or "M" in the code | JV
10 | Discount | 1. Date format should be "YYYY-MM-DD" |  | Use DateUtil.java to prepare the format | JV
11 | Discount | 1. As per requirement, only Percentage will be allowed to modify |  | Changing other values would impact the previous transactions | JV
12 | Discount | 1. Allows to add any text in "start date" field |  | 1. Need to be date in "YYYY-MM-DD" or ALWAYS 2. After the fix, this has to be verified from shopping cart to use the discount | JV
13 | Discount | 1. Allows to add discount for past start dates (with period in days ending before the current date) |  | Need to add date validation | JV
14 | Discount | 1. Allows to add any text in "period in days" field |  | Need to be integer or ALWAYS | JV
15 | Discount | Remove the "Remove" button |  | It will impact the application | JV
16 | Members | 1. Members loyalty points are editable in table UI |  | Make it readonly. This should be always auto-computed based on transaction | JV
17 | Members | Remove the "Remove" button |  | It will impact the application | JV
18 | StoreKeepers | 1. A store keeper is allowed to create another storekeeper |  | This is speculative considering the nature of our application. Consider as low prioriry | JV
19 | Transaction Reports | 1. Clear all the test transaction data and create valid transactions |  |  | JV
20 | Transaction Reports | 1. Provide "Print" button to display the transaction with details that are searched out (as per requirement) |  | Note: The "View" button will display only the selected transaction and not all the details | JV
21 | Transaction Reports | 1. Enter date and hit tab button | It provides tab space in the field instead moving to the next field |  | JV
22 | Transaction Reports | 1. After error message for invalid date format, focus the appropriate field |  |  | JV
23 | Transaction Reports | 1. Provide "Clear" button to clear the search |  |  | JV
24 | Transaction Reports | 1. The top section (filter section" should stretch till the scroll bar |  |  | JV
25 | Transaction Reports | 1. Do not allow "View" without selecting a transaction |  |  | JV
26 | Test Cases | Test Classes missing for StoreKeeper, Discount and Member/Customer |  |  | JV |  | Sabethan | Test class added for storekeeper
27 | Billing | Add first transaction without selecting the product (click '+' button) | Click '+' button showing the confirm dialog box "Do you want to delete the item from the list?" and clicks cancel throws exception |  | Sabethan | FIXED | JV | The table.editingRow was getting reset to -1 due to events trigger. This is fixed now
27 | Category | categoty code should be 3-letter code. Validation should be added when add new category |  |  | Jing |  |  | 3
28 | Vendor | Vendor name should be unique |  | When add new vendor, duplicate vendor names can be added for one category. When save to dat file, the duplicate vendor has not been saved. | Jing |  |  | 5
29 | Product | Add Product dialog should popup in the center position of the app |  |  | JIng |  |  | 5
30 | Product | Product ID is not continuous |  | If user clicks "Cancel", the id will be discarded and not be used again when user added another product. | Jing |  |  | 4
| Discount | spelling - can change "StartDate" to "Start Date" |  |  | Jing |  |  | 5
| Category | It should popup error msg if the user adds duplicate Category Code |  |  | Jing |  |  | 3
| Members | Member ID should be unique |  |  | Jing |  |  | 3
| StoreKeepers | password should be shown as "*********" |  |  | Jing |  |  | 3
| StoreKeepers | StoreKeeper name should be unique |  | currently we can add duplucate storekeeper | Jing |  |  | 3
| StoreKeepers | storeKeeper name should be readonly when edit |  |  | Jing
| billing | When I click "+", it popup the msg "Do u want to delete the item from the list?" | 1. click "+" when product id is blank 2. choose one product, click "+" again | refer to screenshot "billing1" | Jing | FIXED | JV | The table.editingRow was getting reset to -1 due to events trigger. This is fixed now
| billing | Add some products, then click "Close", then click "billing" menu item to open the billing window again, the price column value is changed |  | refer to screenshot "billing2" | Jing | Won't Fix |  | This is a feature to reload the Shopping Cart from the session. To notify the user, a small text (*Shopping Cart restored from session) would appear at the top of the panel for 5 seconds
| billing | choose the wrong discount | 1. buy one product for member "test" 2. confirm 3. discount is 20%. Its correct 4. buy again for member "test" 5. 20% discount is applied again. Its wrong 20% is for member first purchase |  | Jing | FIXED |  | This MemberDiscount is extended to compute the appropriate discount value